MyDas, Workplan for January to April 2018.

To evaluate the proposed methods an OM will be constructed. This will allow the methods to be evaluated as part of an MPs using feedback control. First, however, we will perform cross-tests where the OM and OEM are used to generate data for an assessment methods without feedback to screen the methods. OMs will be constructed using either using life history parameters or data rich stock assessments. In the later case for example using saithe in the North Sea (a data rich stock) to test data poor methods, or data rich stocks such as plaice and sole to evaluate methods for brill and turbot. Different sampling schemes will then be generated using OEMs to simulate data poor assessment datasets. A range of local life histories also need to be considered , e.g. gadoid, flatfish and pelagic stocks.

It is important to ensure buy-in from local experts who are very familiar with the fisheries and the assessments. For example showing them that an empirical HCR performs well for Nth Sea saithe will be of interest but showing that it performs as well for local stocks is very important.

### Task 1
- The species and potential stocks of interest have been identified (https://github.com/laurieKell/mydas/wiki/1-Stock-prioritisation), it is proposed that the final choice of stocks is made at the April meeting, for example after conducting an Ecological Risk Assessment (ERA).
- Allocate Stock to ICES stock assessment categories

### Task 2
- Examples of the different datasets have been collated (https://github.com/laurieKell/mydas/wiki/2-Data-Collation)
- These will now be summarised, e.g. using a Productivity and Susceptibility Analysis
- Productivity can be estimated using FLife,
- Susceptibility can be estimated from the fisheries DB.
- It may be possible to also perform an economic analysis, but this need a bit more thought.
- We will also perform a gap analysis for missing data to better summarise uncertainty.

### Task 3
- Example OM conditioned on life history parameters
- Example OM based on a data rich assessment
- OEM to generate category 1,2,3,4,5& 6 datasets
- Example MSEs based on above
### Task 4
Under this task OMs will be used to select appropriate reference points and methods using a cross-test
- Once the actual stocks and datasets have been identified then case studies for the stocks in Task 1 will be implemented.
- It is important to collaborate with others (e.g. WKLife, WGCSE, Cullen fellowship) and choice of stocks will reflect this.
- NS saithe and NS turbot have cat 1 assessments and these can be used to test category 3,4 assessments by simulating appropriate datasets using an OEM.
- A "flatfish" OM could be used.

### Task 5
Future work; once the reference points are identified under task 4, they will be simulation tested using MSE
## Papers
Proposed papers outlines will be created at https://github.com/laurieKell/mydas/wiki/Outputs